## RU_Outcome3_Revised_Nov2016
S
|  |  | 2017 (Year 1) |  |  | 2018 (Year 2)
ACTIVITY CODE | PLANNED ACTIVITIES YR1 | DELIVERABLE/S | Q2 (June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan-Mar) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | BUDGET NOTES YR1 | COST YR1 ($) | Total Cost ALL | WWF | LL | RU | Consultants | Student bursary | Student field work | Notes
3.1a | Comprehensive literature review of methodologies for CDM and VCS restoration projects conducted by local consultant. | Progress report on literature review for carbon methodologies. A literature review of CDM and VCS methodologies for restoration projects with discussion of the implications for applying to local context (Baviaans) |  | 4473 | 4473.037 | 2237 |  | 2237 |  | Consultant fees for first year for literature review on carbon offsetting methodologies |  | 11183.3333 | 11183
3.1b (DH 2018) | Local consultant to devise methodology from remote sensing analyses and baseline field sampling, starting in YR1 and continuing into YR2 and 3. | Progress reports indicating progress toward devising a carbon methodology using remote sensing and field baselines |  | 4888.8889 | 3733.3333 | 1866.6667 | 3733.3333 | 4666.6667 | 3918.1111 | Consultant fees for first year, including field work, imagery and hardware; 1 month WWF time; 1 trip; 1 workshop; full field sampling (40 points) | [5 empty] | 22807
3.1c | To be devised in Yr2 and Yr3 by local consultants | [10 empty] | 8946.6667 | 8947
3.1d | Engagement to begin in YR1 and continue into yr 5 (will need to extend beyond the methodology development to ensure uptake in phase 2 of carbon tax) | Report summarizing outcomes of government engagement activities conducted in YR1 and implications for getting new methodology approved. |  | 1118.2593 | 0 | 1618.2593 | 0 | 1618.2593 | 0 | 2 weeks WWF time(@4373/month); 1 trip (@500) |  | 18920 | 18920
[10 empty] | Totals |  | 39050 | 39050 |  | 0 | #REF!
3.2a | Baselines conducted by local consultant for 200 ha in Baviaans. | Progress reports on developed Standard Operating Procedure (SOP) and completed sampling for baseline assessment of carbon stocks for 200 ha for Baviaans. Calibration and initial sampling phase to develop Standard Operating Procedure (SOP). Stratification of restoration areas ( 200 hectares). Identify baseline areas and number of plots to be allocated in three phases. Mobilization & training of baselines team and warehouse setup. Baseline sampling with developed SOP. Assess 95% confidence level for stratified areas for phase 1 of sampling. Database update of baselines sampled. Baseline sampling with developed SOP. Assess 95% confidence level for stratified areas for phase 2 of sampling.Database update of baselines sampled. Baseline sampling with developed SOP. Assess 95% confidence level for stratified areas for phase 3 of sampling. Database update of baselines sampled. Final data analysis and report. |  | 20000 | 10000 | 5000 | 5000 | 5000 | 5000 | Local team to conduct baseline assessment for 200ha @ $40 000; researcher to investigate planting protocols (Yondela) |  | 43700 |  |  | 40000 |  | 2000 | 1700
3.2b | Developed during Yr2 | [10 empty] | 1119 | 1119
3.2c | Developed during Yr2 | [10 empty] | 1118 | 1118
3.2d | Developed during Yr2 | [10 empty] | 1118 | 1118
3.2e | Scientific coordination of baselines and methodology | Q2, Q3 and Q4: Reports summarizing scientific coordination activities and evaluation of baseline assessments |  | 2963 | 2222 | 1556 |  | 1556 |  | Scientific supervision of baselines, monitoring and evaluation and reporting @ $6741. If not used then allocated to other activities |  | 19556 |  |  | 19556
[10 empty] | Totals |  | 66611 | 3355 |  | 59556 |  | 2000 | 1700
3.3a | Develop strategy for diversifying livelihoods at Sewefontein (and possibly other communities). Host workshop and meetings with steering committee, local experts and key stakeholders at Sewefontein and surrounding farms, around a strategy for diversifying livelihoods. Work on intergating this plan with the broader development in the Baviaanskloof to open Sewefontein to the opportunity to join structures and gain access to sustainable markets. | Progress report on stakeholder engagement and business plan for livelihoods diversification Report summarizing engagement activities for livelihoods diversification at Sewefontein and detailed business plan for livelihoods diversification, including costs and benefits. Stakeholder engagement plan for Sewefontein. |  | 5318 | 5318 | 5319 |  | 5319 |  | Cost of engagement, meetings, travel and LL time for activities in YR1 @ $15 955 |  | 38866 |  | 31910 |  |  | 5000 | 1956
3.3b | In Yr2 and Yr3 | [10 empty] | 2963 |  | 2963
3.3c | In Yr2 and Yr3 | [10 empty] | 13420 | 13420
3.3d | In Yr2 and Yr3 | [10 empty] | 25390 | 25390
3.3e | In Yr3 | [10 empty] | 20250 | 20250
3.3f | In Yr2 and Yr3 | [10 empty] | 14947 | 14947
3.3g | In Yr3 and Yr4 | [10 empty] | 9000 | 9000
[10 empty] | Totals |  | 124836 | 83007 | 34873 |  |  | 5000 | 1956
3.4a | 1) Document produced on potential rehabilitation options for Sewefontein (and other community farms?), with a cost-benefit and detailed description of techniques and materials. Include some literature on other cases of rehabilitation in overgrazed forested landscapes- lessons learned.Host workshop and meetings with steering committee, local experts and key stakeholders at Sewefontein and surrounding farms. 2) Conduct LFAs and vegetation cover surveys prior to rehabilitation and use to monitor the ecological and land cover impacts of rehabilitation. | Progress report on baseline land (LFA) assessments (Chris will submit this report) and different rehabilitation options that could be suited to Sewefontein; Full report on baseline land functioning assessment results and potential rehabilitation options for Sewefontein |  | 3259 | 741 |  |  |  |  | Baseline LFAs and literature review of different rehab options @ $4000. ADDED THE BALANCE FROM 3.4 TO THIS OUTCOME ($26 711 or about R360 000). |  | 222726 |  | 222726
3.4b | To be conducted near end of Yr2 | na | [7 empty] | na |  | 7859 |  | 3700 |  |  | 3370 | 789
3.4c | Develop a training manual and protocol early in Yr 2 and start training thereafter. | na | [7 empty] | na |  | 8964 |  | 8964
3.4d | Yrs 3 and Yr 4 | Progress on engagement around rehabilitation and potential strategy Report on stakeholder engagement activities (barriers and opportunities and lessons learned for way forward). |  | 5926 | 3703 | 4096 |  | 4096 |  | Cost of meetings, and devising of rehabilitation strategy for Sewefontein @ $13725 (does some of this funding need to be shifted to 3.4a as you should only report on engagement activities here ?). |  | 41175 |  | 41175
3.4e | Engagement and discussions with steering committee, local experts and key stakeholders at Sewefontein and surrounding farms, around viable rehabilitation options for the specific context. Host workshops or individual group meetings. | ? |  | ? | ? | ? |  | ? |  |  | ? | 36278 |  | 36278
[10 empty] | Totals |  | 317002 |  | 312843 |  |  | 3370 | 789
Note on R10: Author_Becky: Yondela
Note on M14: Author_Becky: Mike Powel
Note on C29: Author_Becky: LL please add here what activities and deliverables you think you can achieve in YR1 and amounts needed per quarter