## TIMELINE OUTCOME 1
| COMPLETED | 2017 | [10 empty] | 2018
| PENDING | Q1 |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
SUB-OUPUT | IMPLEMENTING AGENCY | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC
1.2a | RU team | Q1 FEB: Detailed project work plan for 2017-2022 developed
1.2a | Hons 2016/2017 | Q2 APR: Land functioning and rangeland condition baselines @ 5 villages
1.2a | RU + Monde Duma | Q3 AUG: Agrograssing planning; Q1 JAN: Nursery set-up for agrograssing; Q3 JULY: Baselines & start of agrograssing
1.2b/1.2e | RU team | Q1 MAR: Develop Cons./climate smart agric. training programme & ID government partners (DAFF; DEA); Q3 SEPT: Start training in CA/CSA
1.2c | James Gambiza; RU team | Q3 SEPT: CA literature review; Q2 APR: Baseline agriculture assessments and plan for CA implementation
1.2d | RU team; researcher | Q3 SEPT: Start identifying CA demonstration sites & plan for advocacy
1.2f | Doreen Tirivanhu | Q1 FEB: Literature survey for community-based strategies for livelihoods diversification & resilience; Q3 JULY: Identify strategies for improving household resilience at Macubeni (7 principles of resilience)
1.2g | RU team | Q1 JAN: Partners for training in livelihoods diversification strateiges; Q2 APR: Develop livelihoods diversification plan and content of training (LED; Doreen Tirivanhu); Q4 NOV: Start training
1.2h | Charles Chakoma and Monde Duma | Q3 JULY: Literature review: community based sustainable rangeland management practices & rehabilitation
1.2h | Charles Chakoma | Q4 OCT: Preliminary assessment of current livestock management practices and challenges; Q2 APR: Draft plan for community based improved rangeland manaegment; Q3 JULY: Final plan for rangeland management; Q4 OCT: Implement management plan
1.2i | Monde Duma | Q2 APR: Draft plan for participatory rangeland rehabilitation; Q3 JULY: Final plan for rangeland rehabilitation; Q4 OCT: Implement rehabilitation plan
1.5a | RU team | Q3 AUG: Identification of a parralel project for knowledge exchange on participatory monitoring, evaluation and learning; Q1 MAR: Review current strategies for participatory monitoring & learning for communal lands
1.5b | RU team | Q3 JULY: Draft list of indicators for monitoring SLM; Q2 APR: Develop and start implementing participatory MEL programme for Macubeni
1.5c | RU team | Q3 JULY: Establish monitoring sites
1.5d | RU team | Q4 OCT: Training in monitoring at sites

## TIMELINE OUTCOME 2
| COMPLETED | 2017 | [10 empty] | 2018
| PENDING | Q1 |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
SUB-OUPUT | IMPLEMENTING AGENCY | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC
2.5a | Rebecca, James G, Lawrence, Monde N. | Q2 APR: Project inception and engagement with key stakeholders of Macubeni
2.5a | Lawrence & Monde N. | Q2 APR: Stakeholder analysis
2.5b | RU team & researchers | Q3 JULY: Identification of key water and cultivated resources; Q1 JAN: Participatory mapping of key resources and assessment of present-day management (multi-functional landscape)
2.5d | Monde Duma & RU team | Q3 AUG: Engagement with key stakeholders regarding land degradation and rehabilitation plan for Macubeni; Q2 APR: Develop rehabilitation plan
2.5d | Monde Duma & RU team | Q3 SEPT: Preliminary assessment of types and drivers of land degradation; Q1 JAN: Detailed mapping and description of land degradation (types, extent, drivers)
2.1a | RU team | Q3 SEPT: Preliminary engagement with local government regarding partnerships for SLM (DEDEAT; DAFF; LED; DRDL); Q1 JAN: Engage government agencies for technical support with SLM at Macubeni
2.1a | ? | Q1 FEB: Government capacity baselines
2.1b | RU team and community | Q3 JULY: Voluntary advisory group for Macubeni
2.1c | RU team | Q3 SEPT: Preliminary discussions with local government regarding multi-stakeholder forums; Q1 FEB: Multi-stakeholder forum established (government + traditional leaders + NGOs)
2.1d | RU team | Q1 FEB: Develop plan and content of training courses in SLM (also partially covered under outcome 1); Q3 SEPT: Start training courses
2.1e | RU team | Q1 FEB: Covered under 2.5b (key resource management)
2.1e | Community & RU team | Q3 JULY: Develop resource management plan (village level) & start implementation
2.1f | Doreen Tirivanhu + RU team | Q4 NOV: Livelihoods vulnerability baselines; Q3 JULY: Strategy for increasing livelihoods resilience
2.1g & 2.1h | RU team | Q2 APR: Government to integrate SLM & lessons learned from GEF5 project into local decision making (IDP)
2.2a | RU team | Q4 NOV: Start reviewing current government programmes adressing livelihoods vulnerability
2.2e | RU team | Q3 JULY: Develop and start implementing advocacy of SLM
2.3a | RU team | Q4 NOV: Assess community-based natural resource management institutions
2.3a | RU team | Q3 JULY: Plan for providing support and improving capacity of local institutions
2.3b | RU team | Q3 JULY: Strategy for improving government and key stakeholder collaboration

## TIMELINE OUTCOME 3
| COMPLETED | 2017 | [10 empty] | 2018
| PENDING | Q1 |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
SUB-OUPUT | IMPLEMENTING AGENCY | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC
3.1a | WWF | Q3 AUG: Literature review carbon methodologies
3.1b | Dugal Harris | Q2 JUNE: Scoping and testing for new simplified methodology; Q1 JAN: Finalization of new simplified carbon stocks methodology
3.1C | WWF; Cosman Bolus; RU team | Q3 SEPT: Draft Standard Operating Procedures for carbon monitoring developed; Q1 JAN: Finalization of Standard Operating Procedures for quantifying carbon stocks in Thicket
3.1d | WWF | Q3 AUG: Initial engagement with government regarding new carbon methodology and local carbon market; Q1 JAN: Government engagement for new carbon methodology
3.2a | Cosman Bolus & RU | Q3 JULY: Start of carbon baselines; Q1 JAN: Continue carbon baseline assessment 200 ha
3.2e | Mike Powell | Q2 MAY: Scientific coordination outcome 3 continuous
3.3a | LivingLands | Q3 JULY: Preliminary stakeholder engagement regarding GEF5 SLM project and activities; Q1 JAN: Continued stakeholder engagement and diversification of livelihoods strategy
3.3a | LivingLands | Q3 AUG: Draft stakeholder analysis document; Q1 JAN: Finalization of stakeholder analysis
3.3b | LivingLands | Q3 JULY: Evaluate existing institutions and plan to capacitate institutions
3.3h | Rebecca Powell | Q2 MAY: Coordination and evaluation of activities under outcome 3 continuous
3.4a | Chris Jackson | Q2 APR: Baseline Land Functioning Assessment for Sewefontein
3.4a | LivingLands | Q3 SEPT: Nursery set-up for growing plants for rehab and other livelihoods activities (Tchnuganoo); Q2 JUNE: Start of rehabilitation activities on communal farms
3.4b | LivingLands; Yondela Masande, RU team | Q3 JULY: Plan and methods for experimenting on spekboom planting protocols; Q1 JAN: Experimentation on planting protocols for spekboom and technical report on refining planting protocols for spekboom
3.4c | LivingLands | Q3 JULY: Training for rehabilitation
3.4e | LivingLands | Q4 OCT: Rehabiliation plan developed for spekboomveld on communal farms
3.4e | RU team; LivingLands | Q4 OCT: Draft plan for monitoring rehabilitation activities; Q1 JAN: Finalize monitoring plan for rehabilitation activities & start monitoring