## RU Workplan 2016-2020
ANNUAL WORKPLAN 2016 - 2020
| PROJECT TITLE | GEF5: SECURING MULTIPLE ECOSYSTEMS BENEFIT THROUGH SLM IN THE PRODUCTIVE BUT DEGRADED LANDSCAPES OF SOUTH AFRICA
| PIMS NUMBER | 5054
| FUND ID | 62000
| IMPLEMENTING AGENCY | UNITED NATIONS DEVELOPMENT AGENCY
| CONTRACTED PARTY | RHODES UNIVERSITY, SOUTH AFRICA | [9 empty] | United Nations Development Programme (UNDP) Executing agency
EXPECTED CP OUTCOMES | EXPECTED CP OUTPUTS | ACTIVITY CODE | PLANNED ACTIVITY DESCRIPTION | PLANNED ACTIVITY: RESPONSIBLE PERSONS | ANNUAL TARGET | M&E UNDERTAKEN TOWARDS ACHIEVING CP OUPUT/ACTIVITY | INDICATORS: MEASURING SUCCESS OF ACTIVITY | TIMING OF ACTIVITY |  |  |  | OUTPUT RESPONSIBLE PARTY | SOURCE OF FUNDS
OUTCOME 1 | Output 1.1: Improved land-use and livestock/range management practices implemented in two critical riverine systems in the Karoo |  | KAROO
OUTCOME 1 | Output 1.2: Ecologically-viable livestock farming, vegetative cover and range resources management practices adopted in the Eastern Cape over 1300 ha in Macubeni. | 1.2a | Agroforestation & agrograssing of 50 ha over 4 years: Agrograssing using Vetifer grass planted in strips and creation live-fences using suitable tree species that produce fruit (e.g. Carissa bispinosa, Doviala sp.) | James Gambiza; Local municipality; Department of Agriculture; Wildlands Trust Grasspreneur programme | Agroforestation of 50ha across 5 villages | Annual assessment of hectares agroforested, successes and failures and lessons learned | Number of hectares planted successfully on an annual basis | 10 | 10 | 10 | 20 | RU | GEF
OUTCOME 1 |  | 1.2b | Implement conservation agriculture for farmers: no till, permaculture, biocharcoal, improved irrigation, suitable and companion crops. | James Gambiza; Rebecca, Mike, Local consultant 1 & 2; Local Municipality; Local NGO, DA | Conservation agriculture adopted for | Annual review of households implementing conservation agriculture- successes, failures and lessons learned | Number of households successfully implementing conservation agriculture techniques |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.2c | Farmer training workshops held on conservation agriculture (annually) (rangeland management, wetland and soil conservation etc) over 3 years | James, Rebecca, Mike, Local consultant 1 & 2 and others | A workshop held for 50 farmers across 5 villages | Quarterly Progress reports; Field visits | Number of people trained in conservation agriculture across government and non-government sectors |  |  |  |  | RU
OUTCOME 1 |  | 1.2d | Establish of 4 demonstration sites for conservation agriculture | Linked to 1.2D (Local consultant 1 & 2) | Establish 1 demonstration site for a selected village | Quarterly Progress reports; Field visits | Demonstration sites successfully implementing conservation agriculture in multiple forms and in a sustainable manner |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.2e | Promote and training in the adoption of climate smart farming practices | James Gambiza, Rebecca; DA | Adoption for 12-15 farmers across 5 villages | Quarterly Progress reports; Field visits | Number of farmers that have successfully adopted carbon neutral/low carbon farming practices |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.2f | Identify livelihood measures appropriate for increasing community resilience - output 2.5- resource management domains (game farming, sus. Veld management; unemployement; soils; climate etc.); Babu & Reid (2000); | Local consultant 3; James Gambiza | Identification of livelihood measures for increasing community resilience for 50 households across 5 villages | Quarterly Progress reports; Field visits | Resilience Dashboard scores |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.2g | Promote and training in the diversification livelihoods: e.g. vegetable gardens | James Gambiza; Rebecca, Mike, Local consultant 3; Local Municipality; DA | Implementation of diverse livelihood strategies (at least 2-3 strategies) for 50 households across 5 villages? | Quarterly Progress reports; Field visits | Number and diversity of people trained (across ages and across landscape) |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.2g | Implement best practices in rangeland management system for farmers across 5 villages to make up 1300ha; 'Holistic Resource Management' Theory; | Local consultant 4; James Gambiza, ARC | Rangeland management and restoration strategies for 15-20 farmers across 5 villages | Quarterly Progress reports; Field visits | Number of farmers successfully implementing sustainable rangeland management techniques |  |  |  |  | RU | GEF
|  | 1.2h | Implement context specific practices in rangeland restoration for resource management domains; related to output 2.5 - the GIS based system for 5 villages | Local consultant 5; James Gambiza, Gladman, Rebecca etc. | Implement rangeland restoration for up to 500 ha/yr | Quarterly Progress reports; Field visits | Number of hectares receiving improved rangeland management and restoration interventions
|  | 1.2i | Project management and running costs for 1.2
OUTCOME 1 | Output 1.3: Watershed management and SLM practices adopted by farmers in the Olifants River catchment. |  | NOT EASTERN CAPE | [8 empty] | RU
OUTCOME 1
OUTCOME 1 | Output 1.4: A strategy for upscaling SLM practices within the Karoo, Eastern Cape and Olifants landscapes. | Note: | Macubeni will receive $150 000 from UNDP small grants for small grants. $55 000 for rest of activities under 1.4 e.g. developing proposals etc.
OUTCOME 1 |  | 1.4a | Document that demonstrates improved pathways for strategic allocation of finances for SLM based upon lessons learned and best practices written up by Local consultants 3 - 6 under output 2.1 | James, Rebecca, Mike and Local consultants | Best practice booklets on SLM will be produced at end of the project | Reports on successful SLM practices | A best practices booklet produced |  |  |  |  | RU
OUTCOME 1 |  | 1.4b | Develop strategy for sustainability of SLM activities | Mike, James, Rebecca, Lawrence |  |  | Strategy document produced |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.4c | Generate funding proposal for innovative SLM practices which includes stakeholders | Lawrence Sitsika and others | One funded proposal on SLM per year | Number of proposals submitted for funding | Number and success of funding proposals generated |  |  |  |  | RU
OUTCOME 1 |  | 1.4d | Provide support for stakeholder development proposals | Specialist |  |  | Number of households developing proposals |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.4e | Develop a sustainability plan for CBOs, NGOs and government for small grants fund through workshops and help of experts | specialist consultant; find international examples | 1 workshop in 2020 to develop sustainability plan |  | Sustainability plan produced and implemented |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.4f | Develop a strategy for withdrawal of NGOs and Government from communities | Rhodes University social-ecological specialist (Gladman Thondhlana). ID key persons and village resource management committees; get specialists involved. Masters? | Train local champions in each village. | Reports on training workshops held | Development of strategy |  |  |  |  | RU
|  | 1.4g | Management and running costs for 1.4
OUTCOME 1 | Output 1.5: A long-term strategy for participatory monitoring and evaluation by stakeholders (including land users) of the effectiveness of SLM approaches in the Karoo, Eastern Cape and Olifants landscapes. | 1.5a | Review current monitoring programmes for sustainable land management practices | James Gambiza; Local consultants | completed in the 1st year |  | Document summarizing monitoring programmes: theory, strategy and tools on sustainable land management |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.5b | Develop and implement a participatory monitoring and evaluation system; Use 'Local Based Monitoring (LBM)' theory. | Local consultants; James Gambiza, Rebecca, Alta De Vos | Participatory monitoring and evaluation plan produced in 2017 and communicated to local stakeholders | plan reviewed by relevant supervisors of PhD. | Participatory monitoring and evaluation plan produced and implemented through local communties |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.5c | Establish monitoring sites and document the type of data necessary for monitoring SLM activities and the methods & techniques to be employed (wetlands; LFA; SASS5; geotools; monitor veg diversity, erosional areas, soil nutrients, local hydrology etc). | Local consultants; James and Rebecca; part of 1.5B | Establish 5 monitoring sites in 2016 - monitored thereafter annually (monitor rainfall, grazing pressure, plant species, erosional areas, wetland health etc.) | supervision of student; oversee establishment of monitoring sites and regular check-ups on equipment and data being collected; identification of local community members and students to collect data accurately and thoroughly | 5 fully equipped monitoring sites; monitoring data successfully collected and analysed annually; locals trained on data collected and analyzed annually. |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.5d | Training and capacity for monitoring on SLM | Local researchers 4 & 5 + James and Rebecca; Alta | A minimum of 10 people trained per monitoring site per year | Assessment of the competence of local trainees | Mininum of 50 local people trained in varying monitoring skills for SLM/year |  |  |  |  | RU | GEF
OUTCOME 1 |  | 1.5e | Analyse data from monitoring sites | Local consultants; Alta De Vos, James Gambiza + local community members + extension officer | Analyze and report on data from 5 monitoring sites per year; host annual feedback meetings with 2 communities. | Data and report assessed by Local consultants and extension officers | Monitoring reports that have been evaluated by local scientists and the communities; 2 report back meetings held with local communities/year. |  |  |  |  | RU | GEF
|  | 1.5f | Project management and running costs 1.5 | [8 empty] | RU
OUTCOME 2 |  | Notes: | need to host and coordinate national geodatabase on climate, agroecological info.
OUTCOME 2 | Output 2.1: Capacity-building and -development programme for improving SLM knowledge and awareness at local, provincial and national level, including the establishment of multi-stakeholder forums for facilitating a dialogue on SLM and mainstreaming SLM into municipal, provincial and national policy programmes and processes | 2.1a | Gap analysis of technical and instutional capacities for SLM (use UNDP capacity assessment score card) - at beginning of project and just before mid-term review. Do all governance and capacity related work for GEF 5 - 14.1; 4.2; 2.1, baseline assessment of capacity (score cards) | Local consultant 6, James, Mike, Gladman, Rebecca | Report in year 1st year and 2nd on gaps in SLM capacities | Report is peer reviewed and edited | Technical report accepted by advisory-technical committee |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.1b | Establish a strategy for a voluntary advisory group (Machubeni); Identify local leaders and experts and develop a terms of reference for the group | James and Rebecca and local community | Facilitate 2 meetings with voluntary groups per year under the guidance of a Ward councillor + RU team | Minutes from meetings reported and recommendations made | Number of voluntary groups participating per year |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.1c | Develop an organisational strategy for multistakeholder forums in Macubeni: SLM committee; different gov. organizations, water user associations etc. | Local consultant 6; local farmers identified; local NGO (red meat society and others); Ward councillors; input into IDPs process | Strategy document for organization and steering of multistakeholder forums | Steering committee reviews strategy document | Established multistakeholder SLM forum |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.1d | Interdisciplinary training programme: short-courses/training workshops on land degradation and SLM and monitoring over the 3 project sites (Macubeni, Olifants and Karoo) | JAMES/REBECCA/Mike, NGOs | 3 short-courses (1 for each project site) in 2016 and 2018, which are mostly theory based with a small practical component aimed at national to provincial and municipal government + local stakeholders on SLM and rehabiliation | Annual report or overview of training workshops and short-courses- techniques and material used and the type and number of government officials and local community members trained | Number of people trained and skills gained; training handbooks produced |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.1e | Develop and implement village resource management plan (Machubeni)- grazing; streams; homegardens; crops, springs, sand and clay use etc. (Use ARDI method and available info from current MSc students): 1 x 3 day workshop with 25 farmers for all 3 projects sites (R3000/day) | Local researchers 3 - 6 + James, Rebecca + key people identified from Machubeni communities | Develop village management plan for several main resources per annum for 5 villages: | Advisory committee to evaluate resource management plans | Implementation of context specific resource management plans across 5 villages |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.1f | Reduce vulnerability of natural and social capital for households: Baseline studies on vulnerability of communities; reduced vulnerability is covered in other outputs - e.g. implementation of SLM practices, conservation agri., agroforestry/grassing and diversification of livelihoods and 2.1c, g,h, I (place under 2.5) | Local consultant 3; Honours 1; James Gambiza; | Reduced vulnerability achieved for 100 households in 2016 across all 5 villages | Resilience dashboard scores | Increased resilience scores for 100 households per year |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.1g | Integrate lessons learned into mainstream and local decision making (Machubeni)- IDPs at municipal level (1 workshop/ year over 3 yrs) | Local consultants 3 - 6; Steering committee + key specialists to facilitate mainstreaming (Tally Palmer/Christo Fabricious?) | MOA between DEA, agric and municipality and local communities on SLM strategies | Advisory committee to evaluate MOA and lessons learned document | Awareness raised on SLM lessons learned in local municipality, local community forums and catchment forums and possibly national government policy; Small report on degree to which SLM is being considered and adopted into local and national policy; Advocacy on SLM local schools and communities |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.1h | Annual workshops bringing together government agencies to integrate SLM into mainstream decision making (Machubeni); Radio broadcasts (1 simple workshop/year to share results and discuss way forward) | Facilitated by PMU Nationally. Linked to 2.1d; bring in Premier and specialist to facilitate (Christo Fabricious) | Annual workshop on SLM mainstreaming | Documentation of progress and problems discussed in workshops in mainstreaming SLM in government policy | Number of government agencies attending workshops and degree to which SLM is considered for integration into policy and practice |  |  |  |  | UNDP-PMU | GEF
|  | 2.1i | Project management and running costs for 2.1
Use CBA maps already developed for the area; do training that is specific to the site (wetlands etc).
OUTCOME 2 | Output 2.2: Core staff of technical ministries, regional and local extension support departments and land users in the Nama Karoo, Thicket and Savanna biomes trained on the use of improved data, tools and methods of ecosystem livelihood and vulnerability assessments as the basis of decision-making on land use within the context of a green economy. | Note: | This outcome will be integrated into the short-courses and training programme under 2.1
OUTCOME 2 |  | 2.2b | Review existing government programmes + make recommendations as to best practice in livelihoods assessments | Local consultant 6 + Gladman, James etc. | Annual report on existing gov. programmes | Reviewed by supervisors and suggest best practices | Document accepted and adopted by government agencies, local NGOs and communities |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.2c | Develop and disseminate an information kit on sustainable rural livelihoods and vulnerability assessment for Macubeni to government officials and local land users and NGOs etc; annual workshops | Local consultant 3 & 6; Gladman + James | Annual workshops involving social learning on sustainable livelihoods and vulnerability | Report on dissemination strategies on sustainable rural livelihoods and vulnerability assessment | Information kit produced and adopted by local communities and considered and practiced by local government; repository developed (web-based) for people to access info booklet |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.2d | Training workshops for government officials, NGOs, local community (key stakeholders) on tools and methods for assessing livelihood vulnerability (sustainable livelihood framework) for decision making (for all 3 project sites) = only 1 training workshop with 3 gov officials/site) | Gladman and James, Rebecca; Local consultant 3 and 6 | 1 training workshop for 6 gov officials/site | Annual workshop reports - evaluate workshop successes and issues | Number of government officials trained in tools and methods for livelihoods and vulnerability assessments for decision making |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.2f | Dissemination of information on livelihoods and vulnerability to sensitive communities - use theatre?; go to local schools quiz; community forums; take local farmers on local field trips to visit other successful farmers/villages | DAFF extension officer; Dept of rural development; DEA; Dept of Health; NGOs; MSc1; James, Rebecca; Gladman; Lawrence. | 1 Field trip/year including drama productions on sustainable livelihoods, visits to schools and farmer field trips | Report on success and/or issues around information dissemination | Number of advocacy workshops and school competitions held |  |  |  |  | RU | GEF
|  | 2.2g | Use local media to target specific audiences (use local radio or local newspapers, covered by schools quiz above) | James, Gladman, Rebecca, PhD1; PhD4; MSc1. | l radio interview/1 newspaper story and schools quiz | Report on advocacy methods and reception by locals | Number of locals exposed to dissemination of information on sustainable livelihoods |  |  |  |  | RU | GEF
|  | 2.2h | Project management and running costs for 2.2
| 2.3 Structures for coordinated land-use planning and land/ecosystem rehabilitation practices between municipal, provincial and national institutions established | Notes: | Bring in LandCare; Work through local councillor and IDPs (national policy requirement for land-use planning)
OUTCOME 2 |  | 2.3a | Establish and/or provide support to local institutions (village resource management committees) | James; Gladman Thondlana; Local consultant 6; Rebecca | Establish at least 2 village resource management committees | Meet with and evaluate functioning of village resource committees (produce minutes from committee meetings) | Number of VRMCs successfully established for differing resources in the landscape and identification of leader of different groups; Thesis/document on governance issues and recommendations |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.3b | Develop mechanisms to increase collaboration between municipality and other government departments. Use the IDP as a vehicle. | Local consultant 6 | Report on mechanisms for increasing collobration | Steering committee evaluates report | Number of departments successfully collaborating on SLM |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.3c | Strengthen existing multi-stakeholder forums that facilitate dialogue on SLM between stakeholders | Local consultant 6 | local meetings/workshops with multistakeholder groups to facilitate dialogue | Report on multistakeholder forums reviewed by steering committee | Number of workshops held and strength (degree of communication, joint meetings, and action on the landscape) of multistakeholder groups |  |  |  |  | RU | GEF
|  | 2.3d | Project management and running costs for 2.3 | [8 empty] | RU
OUTCOME 2 | Output 2.4: Best practices and lessons learned on SLM in the Karoo, Eastern Cape and Olifants landscapes captured and disseminated nationwide | Note | Part of the GIS system or google docs; develop a best practices manual; multimedia platform | [8 empty] | RU
OUTCOME 2 |  | 2.4a | Develop and publish technical guidelines on SLM best practices: review of success of interventions and develop a handbook describing SLM inverventions, underlying theories and lessons learned as well as manual on the practical procedures and techniques) - linked to 1.4 | Local consultants 3 - 6; James Gambiza + Rebecca + Steering committee | handbook and manual developed | Peer-review of the handbook and manual for corrections and edits | Handbook and manual published |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.4b | Comprehensive manual for SLM implementation in South Africa | PMU coordinates for all 3 project sites | Book template produced 2019 and 2020 | Lead authors identified for chapters of book | Book template produced by end of project - framework |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.4c | Disseminate Best Practice and Lessons Learned from SLM strategies nationwide (see 1.4b): Policy briefs; website; TV broadcasts; conference?; social media | Part of Local consultants activities; PMU must facilitate | Towards end of project. Produce policy briefs in 2019 and 2020 and host conference with all gov departments and contracted parties; advocate via TV and radio; dissemination to local communities through workshops; produce a video | Policy briefs reviewed by steering committee | Number of policy briefs produced and disseminated to key government departments and NGOs; number of local community members briefed on project lessons learned |  |  |  |  | RU | GEF
|  | 2.4d | Project management and running costs
| Output 2.5: A comprehensive GIS-based assessment of socio-ecological resilience to inform ecosystem restoration and SLM in the Karoo, Eastern Cape and Olifants landscapes (look at resources available and being used and assess their current state/health and try and improve funtioning/health). | Notes: | AGIS and BGIS system and water affairs has a GIS system which we should slipstream- incorporate government as much as possible - they have some baseline data. Baseline data that informs others outcomes. Combined effort with CSIR, EWT and RU each doing individual context specific components; Develop Terms of Reference; Develop a central developer who manages all project components; Honours students do baseline surveys
|  | 2.5a | Stakeholder analysis | Lawrence Sisitka | 2016 stakeholder analysis | once-off report | All stakeholders within selected villages engaged with and informed on the overall aim, objectives and workplan for GEF5; Stakeholder analysis report produced
OUTCOME 2 |  | 2.5b | Socio-ecological GIS database: participatory mapping exercise of agroecological resources and degraded areas and culturally valuable areas and base livelihood info. | James, Gladman, Mike, Rebecca, Alta (?), Local consultants 8-10 | Socio-ecological baseline database developed by end of 2016 | Assessments reviewed by local environmental science senior scientists | A database containing data on local livelihoods, vulnerability agroecological and cultural sites and and land degradation characteristics |  |  |  |  | RU | GEF
OUTCOME 2 |  | 2.5c | Develop Resource Management Domains (soils, climate, income, education, vegetation, erosion, wetlands) | James Gambiza; Alta De Vos; Honours students + MSc1 | [7 empty] | RU | GEF
OUTCOME 2 |  | 2.5d | Propose context-appropriate ecosystem rehabilitation interventions | Covered by Local consultant 5; Rebecca; James Gambiza; | Draft restoration plan prepared by end of 2016 | Reviewed by senior Local consultants/steering committee | Report on context appropriate rehabilitation interventions accepted by local community and implementing agencies |  |  |  |  | RU | GEF
|  | 2.5e | Project management and running costs for 2.5
| Output 3.1: Government approved methodology developed for the generation of carbon credits through restoration of spekboomveld | 3.1a | Undertake a comprehensive review of methodolgies for CDM and VCS for restoration projects | Undertake review and analysis: James Reeler | An overview document & recommendations for improved methodology guidelines by end 2016 |  | Overview document prepared and presented to partners |  |  |  |  | WWF
|  | 3.1b | Develop a new methodology for ex ante and ex post carbon stocks | James Reeler, Dugal Harris, Mike Powell | Sampling framework and strategy developed, field sampling completed. | Student progress reports; Field reports for sampling | New carbon methodology documents prepared and submitted to relevant authorities |  |  |  |  | WWF/RU
|  | 3.1c | Develop SOPs (standard operating procedures for thicket restoration) and Protocols for STRP and new methodology | James Reeler | No target 2016 |  | SOP documents developed and circulated to STRP |  |  |  |  | WWF
|  | 3.1d | Engage with Govt agencies to get new methodology approved for carbon tax | Undertake long term engagement with Treasury, DEA, DoE and other relevant government departments: James Reeler | Initiate discussion with DEA & Treasury; obtain conditional endorsement | Quarterly progress reports | Methodology approved under carbon tax for phase 2 (2020) |  |  |  |  | WWF
|  | 3.1e | Project management and running costs for 3.1
| Output 3.2: Carbon baseline sampling and assessments undertaken for 200 hectares in the Baviaanskloof | 3.2a | Baseline C assessment of 200ha using VCS methods | Cosman Bolus/RRRG/James Reeler | Baseline assessment complete |  | Baseline carbon report |  |  |  |  | WWF
|  | 3.2b | Develop monitoring plans for MEASURING C in restored sites | James Reeler | No target 2016 | Annual reports | Measurement monitoring plans developed |  |  |  |  | WWF
|  | 3.2c | Develop monitoring plans for REPORTING C in restored sites | James Reeler | No target 2016 | Annual reports | Reporting templates and structures developed |  |  |  |  | WWF
|  | 3.2d | Develop monitoring plans for VERIFYING C in restored sites | James Reeler | No target 2016 | Annual reports | Verification procedures for methodology developed |  |  |  |  | WWF
|  | 3.2e | Scientific supervision | Scientific oversight for project: Mike Powell | Quarterly scientific coordination discussions | Quarterly report | [5 empty] | RU
|  | 3.2f | Project management and running costs 3.2
| Output 3.3: Project Design Documents for a Baviaanskloof Programme of Activities/Grouped Project prepared and verified. | 3.3a & 3.3b | Engage with Landowners around diversification of livelihoods & develop diversification strategy & implementation for Sewefontein (sustainable farm management plan and planting) do some on commercial lands where not viable on communal lands | Marijn Zwinkels & Justin & others |  | Quarterly reports; field trips; alternative livelihoods plan developed | Number of landowners undertaking alternative livelihoods |  |  |  |  | Living Lands
|  | 3.3c | Assist Sewefontein farmers with setting up legal institutions for carbon off setting and stewardship: Biodiversity stewardship agreement, carbon offsetting institution. | Marijn Zwinkels | Initial legal framework discussions; draft agreement drawn up | Quarterly reports; field trips | Legal institutions established |  |  |  |  | Living Lands
|  | 3.3d | Develop Project Design Documents for 200ha | James Reeler | Undertaken once methodology is finalised | Quarterly reports; field trips | Project document prepared |  |  |  |  | WWF
|  | 3.3e | Verify Project Design Documents via CCBA or VCS or Carbon Tax | External consultant | No target 2016 |  | PDD validated |  |  |  |  | WWF
|  | 3.3f | Verify new project methodology for carbon tax | External consultant | No target 2016 |  | Methodology verified |  |  |  |  | WWF
|  | 3.3g | Id CERs purchasers | James Reeler/WWF | No target 2016 |  | Purchasers secured for CERs generated by project |  |  |  |  | WWF
|  | 3.3h | Register the carbon credits | James Reeler | No target 2016 |  | Credits registered on selected registry (national/voluntary) |  |  |  |  | WWF
|  | 3.3i | Project management and running costs 3.3
| Output 3.4:Restore degraded spekboomveld restored in the Baviaanskloof to deliver multiple ecosystem benefits, including reducing soil erosion, enhanced water infiltration and increased vegetation cover. | 3.4a | Restore 1000ha (co-funding from DEA is almost certain but still need to negotiate): 200ha of spekboom and 800 ha of simple and cheap erosion control, conservation agriculture etc. measures | Justin Gird; Marijn and others (Japie Buckle?) | Plant 56 ha, erosion control and other activities for an additional 200 ha | Review and monitor success of planting and other restoration activities; field visits; quarterly reports | Number of ha planted and receiving restoration works |  |  |  |  | Living Lands/DEA
|  | 3.4b + 3.4c | Tools and methods for planting and refining planting protocols (1 workshop on optimizing planting success) | Justin Gird, Japie Buckle, Marijn, Zwinkels; Marius van der Vyver; Jan Vlok; Mike Powell; Andrew Knipe and others, e.g. farmers | Plant 56ha of spekboom | Review of planting database; field visits; quarterly reports | Number of ha planted |  |  |  |  | Living Lands
|  | 3.4d | Develop and implement training for restoration | Marijn Zwinkels | Undertake training of 12 restoration labourers | Quarterly reports; field trips | Number of restoration labourers trained |  |  |  |  | Living Lands
|  | 3.4e | Restoration project management onsite and landowner engagement | Marijn Zwinkels | Management of Baviaanskloof engagement | Review of planting database; field visits; quarterly reports | Number of ha planted; number of landowners engaged |  |  |  |  | Living Lands
|  | 3.4f | Replant where high mortalities | Marijn Zwinkels | No 2016 target | Review of planting database; field visits; quarterly reports | Mortality counts |  |  |  |  | Living Lands
|  | 3.4g | Project management and running costs 3.4
OUTCOME 4 | Output 4.1: Comprehensive analysis of SLM options, including financial modelling, investigation of market opportunities, cost-benefit analyses and a public expenditure review undertaken |  | CSIR will cover 4.1 this | [8 empty] | UNDP - DEA lead?
OUTCOME 4 |  | 4.1a | Analysis of SLM options from Macubeni |  | Report produced in 2020 | report reviewed by local specialists | Comprehensive report produced |  |  |  |  | RU
OUTCOME 4 | Output 4.2: National and sub-national strategies for mainstreaming of SLM into provincial development and municipal land-use planning policies developed |  | PMU | [8 empty] | UNDP
OUTCOME 4 |  | 4.2a | Expert workshop on national and sub-national strategies for mainstreaming SLM based on lessons from Macubeni | local experts | 1 workshop | Workshop summary report | workshop report produced SLM mainstreaming report produced |  |  |  |  | RU
OUTCOME 4 | Output 4.3: Policy recommendations to mainstream SLM objectives into public expenditure, agricultural subsidies and land reform incentives | 4.3a | Local expert to produce policy recommendations for mainstreaming SLM into public expenditure | local expert | completed in 1 month | Reviewed by steering committee/project managers and others | [5 empty] | RU
OUTCOME 4 | Output 4.4: A national platform on SLM finance and land/ecosystem rehabilitation in place for national dialogue on the role of SLM in the green economy to support the National Coordinating Body for UNCCD to engage more strategically in SLM finance and land/ecosystem rehabilitation |  | PMU
OUTCOME 4 |  |  | Local expert workshop on SLM financing: based on lessons from Macubeni | local expert | [7 empty] | RU
Project management and running costs for outcome 4