## Plan
PhD Work Plan
Very High Resolution Remote Sensing of Carbon Stocks
Dugal Harris
Task | 2016 | [11 empty] | 2017 | [11 empty] | 2018
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Document/publish completed work
Radiometric calibration
Feature selection
Spekboom canopy cover mapping
Data acquisition
Source imagery
Radiometric calibration
Validation
Baviaanskloof field trip
Planning and UAV familiarisation
Execution
UAV image orthorectification and DTM generation
Carbon stock mapping
Literature review
Extend canopy cover mapping to Baviaanskloof
Investigate extraction of plant height from UAV DTM
Feature importance study
Investigate utility of NIR bands and spatial resolution
Build carbon stock regression
Evaluate results
Final write-up
Carbon stock mapping
Introduction and conclusion

## Sheet3
This template by tools4dev is licensed under a Creative Commons Attribution-ShareAlike 3.0 Unported License.